## Sheet1
Patient Management System Risk Register
S/No. | Name of Risk | Risk Owner | Risk Category | Probability (1-3) | Impact (1-3) | PI Score | Risk Response Type | Response Description
| Name of Risk | Name of person who monitors the risk | Group defines the types of risks (technology, financial, staffing, etc.) | Group sourced rough estimate of how likely this is to occur | Group sourced rough estimate of how significant the impact of this risk will be if/when it becomes an issue | Probability multiplied by Impact | Decision made by group on how to respond to this risk | What is the response
1 | Database Connectivity | Developer | Techincal | 1 | 3 | 3 | Mitigate | Assign correct port number
2 | Data backup | User | Techincal | 2 | 2 | 4 | Avoid | Safe the data every day
3 | Error in code | Developer | Techincal | 1 | 3 | 3 | Mitigate | Debug the program online or by onway
4 | Server Down | User | Techincal | 1 | 3 | 3 | Mitigate | Use minimum number of pc